# SIH26242: AI-Assisted RPL Skill Assessment Tool - Implementation Plan

Two-person build plan for Smart India Hackathon Problem Statement 26242

## Winning angle

Most teams will build "upload photo → AI gives score → assessor approves." To stand out, pitch this instead:

An RPL assessment that works for a worker with no internet, limited literacy, and no English, where AI saves the assessor's time but never decides someone's livelihood.

Every feature below supports that line.

## Unique factors, ranked by wow per effort

| # | Feature | Why it wins | Effort |
| --- | --- | --- | --- |
| 1 | Voice-first, multilingual UI (Hindi/Marathi/English, spoken questions, voice answers) | Real RPL candidates often can't type or read well. Use Bhashini (Govt. of India) or Whisper as a fallback. | Medium |
| 2 | Think-aloud evidence: the worker narrates while doing the task | Gives AI and the assessor richer evidence than a silent video, and suits low-literacy users. | Low |
| 3 | Standards-traced rubrics: every checklist item maps to an NOS performance criterion from the real Qualification Pack | Judges see this isn't a generic quiz but built on NSQF itself. | Medium |
| 4 | Confidence-based routing + critical-safety rule: low-confidence items and safety-critical steps (e.g. skipping power isolation) always go to a human | A responsible-AI story. AI recommends, the assessor decides. | Low |
| 5 | Evidence integrity: timestamp, GPS, device ID, SHA-256 hash chain, worker-in-frame check | Directly counters fake submissions. Use a tamper-evident log, not "blockchain" buzzwords. | Low-Med |
| 6 | Declaration-vs-performance consistency score | Flags people who claim 10 years but fail basic tool identification. | Low |
| 7 | Gap-to-pathway: "needs improvement" skills link to bridge-training suggestions and the next NSQF level | Turns the report into a growth plan, not just pass/fail. | Low |
| 8 | QR-verifiable certificate (DigiLocker / Skill India integration-ready, mocked in demo) | Employers can verify instantly. | Low |
| 9 | Assessor time-saver: AI flags jump the video to the exact timestamps of concern | Addresses the real bottleneck, assessor capacity. | Medium |
| 10 | Fairness dashboard: score distribution by language, gender, region | Shows you thought about bias. Good for jury Q&A. | Low (if time) |

Build 1-8 as core. Treat 9-10 as stretch goals.

## Scope decision (important for feasibility)

Build a config-driven "Trade Pack" system: one JSON per trade containing tools, safety questions, tasks, rubric, NOS mapping, and level thresholds. Fully implement Electrician (from the problem statement) and one more trade (plumber or welder). This proves it scales to any trade without code changes, which is a strong pitch point and avoids overbuilding.

Hand-curate 2-3 Qualification Packs from the public QP documents on NQR or the relevant Sector Skill Council sites instead of scraping everything. Check the actual assessment criteria and pass thresholds there rather than inventing them.

## Stack

- Frontend (both apps): React + Vite PWA, Workbox, IndexedDB (Dexie), i18next

- Backend: FastAPI (Python), PostgreSQL + pgvector, S3-compatible storage (Supabase or MinIO)

- AI: LLM with structured JSON output for mapping and scoring, RAG over QP/NOS text, a vision model on extracted keyframes, ASR for narration

- Hosting: Vercel (frontend), Render or Railway (backend), free tiers

## How you two stay in sync

- Monorepo with /contracts (OpenAPI spec + JSON schemas) as the single source of truth. Nobody changes it without telling the other.

- Mock server first. Person B publishes a mock API (Prism or FastAPI stubs) on Day 2, so Person A never waits for the real backend.

- Shared status state machine, used by both sides:

DRAFT → DECLARED → MAPPED → PLAN_READY → IN_PROGRESS → SUBMITTED → AI_ANALYZED → UNDER_REVIEW → (REASSESS | REVIEWED) → APPROVED / REJECTED

- Shared entities: Worker, Declaration, QPMatch, AssessmentPlan, Task, Evidence, AIAnalysis, AssessorReview, CompetencyReport, Decision.

- Offline sync rules (agree on these on Day 1):

  - Client-generated UUIDs and an idempotency key on every write

  - Evidence is append-only

  - Worker data uses last-write-wins with a version field

  - Assessor and approval fields are server-authoritative

  - Uploads are chunked and resumable

- A 15-minute daily sync, plus a joint integration test at the end of every phase.

## Who builds what

### Person A: Field side (all frontends and offline)

- Worker PWA: registration, declaration, voice input, i18n

- Assessment player: tool-ID, safety MCQs, checklists, photo/video/audio capture with GPS and timestamp

- Assessment pack download (tasks cached before going offline)

- Offline outbox, sync engine, resumable uploads, conflict handling

- Assessor portal UI: queue, evidence viewer with AI flags, override/comment/reassess, final approval

- Report and certificate views

### Person B: Brain side (backend, AI, data)

- DB, auth (mobile OTP), roles (worker / assessor / authorized assessor)

- Trade Pack schema and QP/NOS knowledge base with embeddings

- NSQF mapping: top-3 matches with confidence and reasoning

- Assessment plan generator from trade pack plus mapping

- Evidence analysis pipeline: keyframe extraction, vision checks, ASR on narration, rubric scoring

- Scoring engine: deterministic weighted rubric, where AI only fills item scores and never decides pass/fail

- Integrity layer (hashing, audit log), competency report generator, PDF with QR certificate and verify page, optional fairness stats

The split is frontend/backend, so the API contract is the only seam. If one of you is stronger in AI, swap the AI pipeline to that person and move the report generator to the other.

## Phased timeline (5 weeks, adjust to your deadline)

| Phase | Person A | Person B | Joint check |
| --- | --- | --- | --- |
| 0 (Days 1-2) | Wireframes, repo, PWA shell | Schemas, OpenAPI, mock server | Contract locked |
| 1 (Week 1) | Registration + declaration + voice + i18n | DB, auth, QP knowledge base, trade packs | Worker registers against the real API |
| 2 (Week 2) | Assessment player + media capture | NSQF mapping + plan generator | Declare → mapped → tasks appear |
| 3 (Week 3) | Offline engine + assessor queue | AI evidence analysis + scoring + integrity | Airplane-mode test: full assessment offline, reconnect, AI results show up |
| 4 (Week 4) | Assessor review UX, report view | Report/PDF/QR, NSQF level logic, approval workflow | Full flow end to end |
| 5 (Week 5) | Polish, demo data | Accuracy tuning, deployment | Test with a real electrician or ITI student, rehearse |

## Scoring logic

- Auto-scored: MCQs, tool identification, checklist consistency

- AI-assisted with confidence: photo/video steps and narration

- Human-only: anything below your confidence threshold, plus critical safety steps

- NSQF level suggestion: based on the matched QP's level and score bands, so a borderline candidate gets "pass at Level N-1 + bridge training" instead of a flat fail

## Risks and cut-list

| Risk | Mitigation |
| --- | --- |
| Vision AI can't truly judge wiring quality | Position it as evidence triage (PPE visible? insulation? colour coding? sequence?). Frame it honestly in the pitch. |
| Offline sync bugs | Offline-first for capture only. Queue AI steps for when you're online. |
| API cost or rate limits | Cache AI results, use free credits, and pre-compute for demo data. |
| Language ASR quality | Always show the transcript to the worker for confirmation. |
| Time crunch | Cut order: fairness dashboard → second trade → QR verify page. Never cut: offline test, assessor override, voice input. |

## Metrics for the jury

Run a small mock pilot and report real numbers: AI-vs-assessor score agreement, assessor review time with and without AI flags, and completion rate in voice mode vs typed mode. Even 10-15 test candidates give you credible evidence. Don't quote statistics you haven't measured.

## Social impact

- Most of India's workforce is informal and has skills without papers. Certification opens access to better wages, formal jobs, credit, and safety training.

- Assessor capacity is the bottleneck for RPL, and AI-assisted triage lets each assessor handle more candidates without lowering quality.

- Voice-first and offline-first design reaches workers that typical digital tools miss.

## 3-minute demo script

- A worker speaks their trade in Hindi or Marathi.

- AI maps the worker to an NSQF job role with a confidence score.

- Switch to airplane mode and complete a task with a narrated video.

- Reconnect, and the data syncs.

- The assessor sees AI flags, overrides one score, and approves.

- A QR-verified competency report appears, with gaps and a pathway.